## WBS with Gantt Chart
Work Breakdown Structure With Gantt Chart Template
Project Title | miniTA
Project Manager | Nguyễn Cao Triết
Date | 2026-10-20 | [5 empty] | Phase One | [17 empty] | Phase Two | [6 empty] | Phase Three | [9 empty] | Phase Four |  |  |  |  | Phase Five | [9 empty] | Phase Six
WBS Number | Task Title | Task Owner | Start Date | Due Date | Duration | % of Task Complete | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1.0 | PA1: Initiation & Planning |  | 2026-10-16 | 2026-10-21 | 4
1.1 | Define product vision and business scope |  | 2026-10-16 | 2026-10-19 | 2
1.1.1 | Write Preliminary Problem Statement & Product Position | Mẫn | 2026-10-16 | 2026-10-16 | 1 | 100% | bar: Week 3 F
1.1.2 | Define Stakeholders, Users, and MoSCoW Feature List | Mẫn | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.1.3 | Define Out-of-scope list and product boundaries | Mẫn | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.2 | Design preliminary architecture and technology solution |  | 2026-10-19 | 2026-10-19 | 1
1.2.1 | Draw C4 System Context diagram | Anh | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.2.2 | Define Technology Stack and Operating Environment | Anh | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.2.3 | Define Branching, PR, CI conventions and Repository Structure | Anh | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.3 | Build WBS, effort estimates, and risk register |  | 2026-10-19 | 2026-10-20 | 2
1.3.1 | Build Work Breakdown Structure (Levels 1-3) | Nghi | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.3.2 | Synthesize effort estimates from all members | Nghi | 2026-10-19 | 2026-10-19 | 1 | 0% | bar: Week 4 M
1.3.3 | Create Risk Register | Nghi | 2026-10-20 | 2026-10-20 | 1 | 0% | bar: Week 4 T
1.4 | Project planning and document integration | Triết | 2026-10-20 | 2026-10-21 | 2
1.4.1 | Create Schedule | Triết | 2026-10-20 | 2026-10-20 | 1 | 0% | bar: Week 4 T
1.4.2 | Define Roles, Backups, and Cost Estimate | Triết | 2026-10-20 | 2026-10-20 | 1 | 0% | bar: Week 4 T
1.4.3 | Consolidate PA1 document | Triết | 2026-10-21 | 2026-10-21 | 1 | 0% | bar: Week 4 W
2.0 | PA2: Requirements Specification |  | 2026-10-22 | 2026-10-30 | 7
2.1 | Write Business Rules & Domain requirements | Mẫn | 2026-10-22 | 2026-10-23 | 2 | 0% | bar: Week 4 R to Week 4 F
2.2 | Write Functional (FR) & Non-functional Requirements (NFR) | Triết | 2026-10-23 | 2026-10-26 | 2 | 0% | bar: Week 4 F to Week 5 M
2.3 | Draw Use Case Diagram & Write Use Case Specifications | Mẫn | 2026-10-26 | 2026-10-27 | 2 | 0% | bar: Week 5 M to Week 5 T
2.4 | Design initial UI Mockups for Applicant Portal | Anh | 2026-10-27 | 2026-10-28 | 2 | 0% | bar: Week 5 T to Week 5 W
2.5 | Design initial UI Mockups for Recruiter Inbox | Anh | 2026-10-28 | 2026-10-29 | 2 | 0% | bar: Week 5 W to Week 5 R
2.6 | Create Requirements Traceability Matrix | Nghi | 2026-10-29 | 2026-10-30 | 2 | 0% | bar: Week 5 R to Week 5 F
3.0 | PA3: Software Design |  | 2026-11-02 | 2026-11-13 | 10
3.1 | Design C4 Container & Component Diagrams | Anh | 2026-11-02 | 2026-11-03 | 2 | 0% | bar: Week 6 M to Week 6 T
3.2 | Write Architecture Decision Records (ADRs) | Triết | 2026-11-03 | 2026-11-04 | 2 | 0% | bar: Week 6 T to Week 6 W
3.3 | Design Database Entity-Relationship Diagram (ERD) | Nghi | 2026-11-04 | 2026-11-05 | 2 | 0% | bar: Week 6 W to Week 6 R
3.4 | Define Database Schema constraints & indexing | Nghi | 2026-11-06 | 2026-11-09 | 2 | 0% | bar: Week 6 F to Week 7 M
3.5 | Design detailed Class & Sequence Diagrams | Triết | 2026-11-09 | 2026-11-11 | 3 | 0% | bar: Week 7 M to Week 7 W
3.6 | Finalize detailed UI/UX Screen Flows | Anh | 2026-11-11 | 2026-11-13 | 3 | 0% | bar: Week 7 W to Week 7 F
4.0 | PA4: Test Planning |  | 2026-11-16 | 2026-11-20 | 5
4.1 | Formulate overall Test Plan Strategy (Levels & Types) | Mẫn | 2026-11-16 | 2026-11-16 | 1 | 0% | bar: Week 8 M
4.2 | Define Test Environment & Defect Management process | Mẫn | 2026-11-16 | 2026-11-17 | 2 | 0% | bar: Week 8 M to Week 8 T
4.3 | Apply Boundary Value Analysis & Equivalence Partitioning | Nghi | 2026-11-17 | 2026-11-18 | 2 | 0% | bar: Week 8 T to Week 8 W
4.4 | Write detailed Test Cases for Applicant workflows | Nghi | 2026-11-18 | 2026-11-19 | 2 | 0% | bar: Week 8 W to Week 8 R
4.5 | Write detailed Test Cases for Recruiter workflows | Nghi | 2026-11-19 | 2026-11-20 | 2 | 0% | bar: Week 8 R to Week 8 F
5.0 | PA5: Implementation, Testing & Deployment |  | 2026-11-23 | 2026-12-04 | 10
5.1 | F01: Account & Role Management |  | 2026-11-23 | 2026-11-24 | 2 | 0%
5.1.1 | Implement Auth APIs & Database integration | Nghi | 2026-11-23 | 2026-11-24 | 2 | 0% | bar: Week 9 M to Week 9 T
5.1.2 | Build Login & Account UI components | Anh | 2026-11-24 | 2026-11-24 | 1 | 0% | bar: Week 9 T
5.2 | F02: Job Posting Management |  | 2026-11-24 | 2026-11-25 | 2 | 0%
5.2.1 | Implement Job CRUD APIs | Triết | 2026-11-24 | 2026-11-25 | 2 | 0% | bar: Week 9 T to Week 9 W
5.2.2 | Build Job Management UI components | Anh | 2026-11-25 | 2026-11-25 | 1 | 0% | bar: Week 9 W
5.3 | F03: Rubric Builder & AI Job-Intake |  | 2026-11-25 | 2026-11-26 | 2
553.1 | Integrate LLM API & JSON Schema validation | Triết | 2026-11-25 | 2026-11-26 | 2 | 0% | bar: Week 9 W to Week 9 R
5.3.2 | Build Rubric Configuration UI | Anh | 2026-11-26 | 2026-11-26 | 1 | 0% | bar: Week 9 R
5.4 | F04: Candidate Application Portal |  | 2026-11-26 | 2026-11-27 | 2
5.4.1 | Implement Application submission APIs & File Upload | Nghi | 2026-11-26 | 2026-11-27 | 2 | 0% | bar: Week 9 R to Week 9 F
5.4.2 | Build Public Application Form UI | Anh | 2026-11-27 | 2026-11-27 | 1 | 0% | bar: Week 9 F
5.5 | F05: Candidate Status Portal |  | 2026-11-27 | 2026-11-30 | 2
5.5.1 | Implement Email Service & Magic-link logic | Nghi | 2026-11-27 | 2026-11-30 | 2 | 0% | bar: Week 9 F to Week 10 M
5.5.2 | Build Status Tracking UI | Anh | 2026-11-30 | 2026-11-30 | 1 | 0% | bar: Week 10 M
5.6 | F06: Automated CV Extraction & Matching |  | 2026-11-30 | 2026-12-01 | 2
5.6.1 | Implement PDF text extraction logic | Nghi | 2026-11-30 | 2026-12-01 | 2 | 0% | bar: Week 10 M to Week 10 T
5.6.2 | Implement Rule-based text matching engine | Triết | 2026-12-01 | 2026-12-01 | 1 | 0% | bar: Week 10 T
5.7 | F07: Applicant Inbox Workflow |  | 2026-12-01 | 2026-12-02 | 2
5.7.1 | Implement candidate filtering & human scorecard APIs | Triết | 2026-12-01 | 2026-12-02 | 2 | 0% | bar: Week 10 T to Week 10 W
5.7.2 | Build Applicant Inbox UI | Anh | 2026-12-02 | 2026-12-02 | 1 | 0% | bar: Week 10 W
5.8 | F08: Recruitment Dashboard |  | 2026-12-02 | 2026-12-03 | 2
5.8.1 | Implement statistics aggregation APIs | Triết | 2026-12-02 | 2026-12-03 | 2 | 0% | bar: Week 10 W to Week 10 R
5.8.2 | Build Dashboard Charts UI | Anh | 2026-12-03 | 2026-12-03 | 1 | 0% | bar: Week 10 R
5.9 | Quality Assurance & Dev Ops |  | 2026-12-02 | 2026-12-04 | 3
5.9.1 | Write automated Unit Tests (Pytest/Vitest) | Mẫn | 2026-12-02 | 2026-12-03 | 2 | 0% | bar: Week 10 W to Week 10 R
5.9.2 | Execute System Testing & Log defects | Mẫn | 2026-12-03 | 2026-12-04 | 2 | 0% | bar: Week 10 R to Week 10 F
5.9.3 | Configure GitHub Actions CI workflow | Nghi | 2026-12-03 | 2026-12-04 | 2 | 0% | bar: Week 10 R to Week 10 F
5.9.4 | Deploy Database & App Containers to Cloud | Triết | 2026-12-04 | 2026-12-04 | 1 | 0% | bar: Week 10 F
6.0 | Final: Presentation & Demo |  | 2026-12-07 | 2026-12-11 | 5
6.1 | Prepare presentation slide deck | Mẫn | 2026-12-07 | 2026-12-08 | 2 | 0% | bar: Week 11 M to Week 11 T
6.2 | Prepare live-demo script and fallback video | Anh | 2026-12-08 | 2026-12-10 | 3 | 0% | bar: Week 11 T to Week 11 R
6.3 | Rehearse 15-minute presentation | Triết | 2026-12-10 | 2026-12-11 | 2 | 0% | bar: Week 11 R to Week 11 F
CLICK HERE TO CREATE IN SMARTSHEET